## Dashboard
EOT Claim Report – Industrial Projects
Prepared by: Behzad Mousavi ¦ M.Sc. Industrial Engineering ¦ Project Controls Specialist
Project Name: | Your Project Name
Contractor: | Your Company Name
Report Date: | 2025-12-30
Planned Project Duration (Days): | Your Project Duration
Original Completion Date: | 2025-12-29
Forecasted Completion Date: | 2025-12-29
Delay in Employer’s Approval of P&ID | 16
Delay in Equipment Delivery due to Sanctions | 10
Unforeseen Site Conditions (Soil) | 17

## Delay Events
Row | Start Date | End Date | Duration (Days) | Delay Reason | Category | Supporting Docs
1 | 2025-03-10 | 2025-03-25 | 16 | Delay in Employer’s Approval of P&ID | Employer Risk | Letter Ref: EMP-2025-031
2 | 2025-06-01 | 2025-06-10 | 10 | Delay in Equipment Delivery due to Sanctions | Force Majeure / External | Vendor PO #V2025-889
3 | 2025-08-20 | 2025-09-05 | 17 | Unforeseen Site Conditions (Soil) | Employer Risk (FIDIC 4.12) | Geotech Report GR-2025-07
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Program Snapshot
Activity | Baseline Finish | Forecast Finish | Variance
Engineering Design | 30-Apr-2025 | 15-May-2025 | 15
Equipment Procurement | 30-Jul-2025 | 10-Sep-2025 | 42
Mechanical Installation | 30-Oct-2025 | 20-Nov-2025 | 21
Pre-Commissioning | 30-Nov-2025 | 15-Dec-2025 | 15
Final Handover | 15-Dec-2025 | 08-Jan-2026 | 24

## Claim Summary
EOT Claim Summary
Total Delay Days Requested: | 43
Recommended Extension of Time: | 43 Calendar Days
Submitted by: | Behzad Mousavi – Project Controls Consultant
Date: | 2025-12-30
Contact: sbmousavi.planning@gmail.com
Payment: USDT (TRC-20) accepted for full version
This template is based on real EPC project experience in oil & gas.
Full version includes automated logic, formatting, and professional layout

## User Guide
Change the cells that are highlighted in red according to your project information.